## WEEK04
WBS ID | TASK | DELIVERABLES | OWNER | START | END | ESTIMATED COST (RM) 11_NOV | ## Integration Notes
1.1 | Gather System Requirement | Project proposal document | MAS | 2025-10-06 | 2025-10-08 | 200
1.2 | Obtain approval for initial plan | Approved Project Scope | MAS | 2025-10-09 | 2025-10-10 | 100 | - High-cost tasks include Model Development & Evaluation and Dashboard Design & Implementation.
2.1 | Collect raw dataset | Collected dataset | FAIZ | 2025-10-13 | 2025-10-15 | 160 | - These tasks occur around key milestones such as "Model trained" and "Dashboard completed".
2.2 | Clean and preprocess data | Cleaned and Structured data file | FAIZ | 2025-10-16 | 2025-10-17 | 50 | - Linking costs to schedule helps ensure resources are available when needed and highlights potential budget risks.
3.1 | Select suitable algorithms and techniques | Model Design Blueprint | ANAS | 2025-10-20 | 2025-10-22 | 160 | - Observing cost peaks allows better planning and contingency management.
3.2 | Split data into training and testing sets | Dataset Partition Files | ANAS | 2025-10-23 | 2025-10-25 | 50
4.1 | Train model using training dataset | Trained Model File | ADIB | 2025-10-27 | 2025-10-29 | 100
4.2 | Optimize model performance | Performance Optimization Summary | ADIB | 2025-10-30 | 2025-10-31 | 200
5.1 | Evaluate model accuracy and performance metrics | Evaluation Report | MAS | 2025-11-03 | 2025-11-04 | 160
5.2 | Conduct error analysis | Confusion Matrix / Accuracy Chart | MAS | 2025-11-05 | 2025-11-07 | 120
6.1 | Design dashboard user interface | Functional Dashboard Interface | ANAS | 2025-11-14 | 2025-11-17 | 180
6.2 | Implement data visualization components | Visualization Screenshots / UI Mockups | FAIZ | 2025-11-18 | 2025-11-19 | 240
7.1 | Conduct system and functional testing | Testing Report | ADIB | 2025-11-22 | 2025-11-23 | 150
7.2 | Perform user acceptance testing (UAT) | Bug Fix Log | ADIB | 2025-11-23 | 2025-11-24 | 120
8.1 | Prepare final project report | Final Project Report | MAS | 2025-11-29 | 2025-11-30 | 150

## Week 05 – Cost & Resources.
WBS ID | TASK | RESOURCE TYPE | RESOURCE NAME | QUANTITY/ HOURS | DESCRIPTION
1.1 | Gather System Requirement | Human | Project Manager, Analyst | 10 hrs | Identify system needs, define objectives, and gather user requirements.
1.2 | Obtain approval for initial plan | Human | Project Manager, Stakeholders | 5 hrs | Present and get approval for proposed project plan and resources.
2.1 | Collect raw dataset | Human, Data | Data Engineer, Public Dataset | 8 hrs | Source, download, and organize raw data for model training.
2.2 | Clean and preprocess data | Software | Python, Excel | 15 hrs | Handle missing values, normalize, and transform data into usable format.
3.1 | Select suitable algorithms and techniques | Human | Data Scientist | 8 hrs | Research and determine appropriate ML algorithms and evaluation methods.
3.2 | Split data into training and testing sets | Software | Python | 4 hrs | Divide dataset into training and testing portions for validation.
4.1 | Train model using training dataset | Hardware | GPU Instance | 20 hrs | Train the selected model using the prepared dataset.
4.2 | Optimize model performance | Human | Data Scientist | 10 hrs | Adjust model parameters and improve accuracy and efficiency.
5.1 | Evaluate model accuracy and performance metrics | Human, Software | Team members, Evaluation Tools | 8 hrs | Assess performance using metrics (precision, recall, F1-score, etc.).
5.2 | Conduct error analysis | Human | Team members | 6 hrs | Identify and analyze errors or biases in model predictions.
6.1 | Design dashboard user interface | Human, Software | UI/UX Designer, Figma | 12 hrs | Design user-friendly dashboard layout and components.
6.2 | Implement data visualization components | Software | Frontend Developer, D3.js/Plotly | 16 hrs | Develop visual charts and integrate into the dashboard.
7.1 | Conduct system and functional testing | Human | QA Tester | 10 hrs | Test system functions, fix bugs, and validate performance.
7.2 | Perform user acceptance testing (UAT) | Human | QA Team, End Users | 8 hrs | Confirm system meets user needs before deployment.
8.1 | Prepare final project report | Human | Project Manager, Technical Writer | 10 hrs | Document project results, findings, and recommendations.
WBS ID | TASK | HOURS | Rate (RM/hr or flat) | Total Cost (RM)
1.1 | Gather System Requirement | 10 hrs | 20 | 200
1.2 | Obtain approval for initial plan | 5 hrs | 20 | 100
2.1 | Collect raw dataset | 8 hrs | 20 | 160
2.2 | Clean and preprocess data |  | 50 (flat license) | 50
3.1 | Select suitable algorithms and techniques | 8 hrs | 20 | 160
3.2 | Split data into training and testing sets |  | 50 (flat license) | 50
4.1 | Train model using training dataset | 20 hrs | 5 | 100
4.2 | Optimize model performance | 10 hrs | 20 | 200
5.1 | Evaluate model accuracy and performance metrics | 8 hrs | 20 | 160
5.2 | Conduct error analysis | 6 hrs | 20 | 120
6.1 | Design dashboard user interface | 12 hrs | 15 | 180
6.2 | Implement data visualization components | 16 hrs | 15 | 240
7.1 | Conduct system and functional testing | 10 hrs | 15 | 150
7.2 | Perform user acceptance testing (UAT) | 8 hrs | 15 | 120
8.1 | Prepare final project report | 10 hrs | 15 | 150
Total |  |  |  | RM 2120
Cost Category | Example Items | Subtotal (RM)
Human Resources | Team members, assistants | 1500
Hardware / Cloud | GPU, storage | 300
Software / Licenses | Tools or subscriptions | 200
Communication | Online meetings | 150
Total Estimated Budget |  | 2150